## Slide 1: Agile Estimation
Dan Berlin
daniel.l.berlin@gmail.com

## Slide 2
Wikipedia: Estimation is the calculated approximation of a result which is usable even if input data may be incomplete or uncertain.

## Slide 3: Common Problems with Estimation
Manager: “How long will this take?”
Engineer: “Do you mean if I worked full time on JUST THIS, or with my other work?”
Calendar time is not a measure of effort.

## Slide 4: Common Problems with Estimation
Manager: “Joe said it would take three weeks.”
Engineer: “What!? He’s wrong, the MountainCrusher library already does that, and I have a copy right here.”
One’s mountain is another’s molehill.

## Slide 5: Common Problems with Estimation
Manager: “Why is this taking so long!? You said this would only be two days!”
Engineer: “I said that 4 months ago! The current system architecture makes this feature much harder to build.”
Estimates have a short shelf-life.

## Slide 6: Common Problems with Estimation
Engineer: “I don’t know how long it will take until I know every detail.”
Manager: “I gave you everything we have, now just take a guess.”
You will never know every detail up front.

## Slide 7: Common Problems with Estimation
Manager: “Now how long will it take to do Z?”
Engineer: “Well, I haven’t even done B yet, so I don’t have any way to know!”
Manager: “How long for B?”
Engineer: “About a week.”
It is easier to estimate in the near future.

## Slide 8
Agile estimation avoids these common problems (and more) by taking a more practical approach to estimating work.

## Slide 9: How to Estimate
Define your work (User Story Modeling)
Collaborate and compare to increase accuracy (Planning Poker, Relative Sizing)
Use a unit of work, not time (Story Points)
Measure real progress (Velocity)
Adapt to change (Re-estimation)

## Slide 10: User Story Modeling
(Who) wants (what) so that (why)
Keep your user stories small
A story is a conversation starter, and gets more detailed over time

## Slide 11: User Story Modeling
GOOD:
Billing wants to see a summary page of all unpaid accounts, so that they can collect payments.
BAD:
Our company wants a new website to increase sales.
Users want rounded corners on the search button.
Good stories satisfy INVEST:
  Independent
  Negotiable
  Valuable
  Estimable
  Small
  Testable

## Slide 12: User Story Modeling: Acceptance Criteria
Story: Users want to import music from a folder so that they can include their own music in the library.
Given a user is on the "Library Folder" screen
When the user clicks Add Then the Add Folder screen shows a radio option for "Search for Music”
When the user saves a folder with "Search for Music" checked Then the folder is added to the list of folders.

## Slide 13: Planning Poker
After all the stories are written, prioritize!
Choose which stories to estimate first
Estimate by consensus
  Have story owner give a brief overview
  Only open discussion if the estimates don’t match
  Record estimating assumptions

## Slide 14: Story Points
Story Points are a unit of size/complexity, not duration
Relative sizing: estimate based on other stories
An alternative unit: Ideal Days
Don’t worry: You will calculate duration later…

## Slide 15: Story Backlog
This is just a bucket for all your stories
Keep it organized!
Pull stories off this list to create an iteration

## Slide 16: Iteration 1
Usually 2-4 weeks
Do high risk / high priority work first
Make sure everyone can be kept busy
How much can you do in one iteration?
  Take the estimates off the stories at first
  Try not to kill yourselves…

## Slide 17: Team Velocity
Velocity is the number of points you can complete in one iteration
If you can demo it, you get credit. No partial credit!
Over time this number will stabilize (usually after 3 iterations)
Points of work / Velocity * Iteration length =
Calendar Time!

## Slide 18: Re-estimation
Re-estimate when you have new information that affects your previous estimates
Review all your story estimates before each iteration
Re-estimate if you change a story

## Slide 19: Lab - Planning Poker
Break up into groups
Define roles you will represent:
  Business users (2) and team members (design, dev, QA, etc)
We work at Expedia.com and have 20 million customers. You are doing an add-on for the Customer Service team. Do a planning poker for this user story:
“Customer Service wants to search for customers by their first and last name, so that they can quickly retrieve customer information when on a call.”