## Slide 1: Agile Estimation and Planning
Dan Berlin
daniel.l.berlin@gmail.com

## Slide 2: What is Estimation?
Wikipedia: Estimation is the calculated approximation of a result which is usable even if input data may be incomplete or uncertain.
In software engineering, estimation is the process of speculating the amount of effort required to complete a task or set of tasks.

## Slide 3: Why Do We Estimate Work?
Resource Planning
Cost vs. Benefit Analysis
Coordination with other projects
What else?

## Slide 4: Why Do We Really Estimate Work?
To avoid stressful situations!!

## Slide 5: Common Problems with Estimation
Calendar time is not a measure of effort.
Manager: “How long will this take?”
Engineer: “Do you mean if I worked full time on JUST THIS, or with my other work?”

## Slide 6: Common Problems with Estimation
One’s mountain is another’s molehill.
Manager: “Joe said it would take three weeks.”
Engineer: “What!? He’s wrong, the MountainCrusher library already does that, and I have a copy right here.”

## Slide 7: Common Problems with Estimation
Estimates have a short shelf-life.
Manager: “Why is this taking so long!? You said this would only be two days!”
Engineer: “But I said that 4 months ago! The current system architecture makes this feature much harder to build.”

## Slide 8: Common Problems with Estimation
It is easier to estimate the near future.
Manager: “How long will it take to do Z?”
Engineer: “I haven’t even done B yet!”
Manager: “How long for B?”
Engineer: “Hmm… Maybe a week or so.”

## Slide 9
Agile estimation avoids these common problems (and more) by taking a more practical approach to estimating work.

## Slide 10: The Agile Estimation Process
Define your work (User Story Modeling)
Estimate collaboratively (Planning Poker)
  Use a unit of work, not time (Story Points)
  Increase accuracy with relative sizing
Measure real progress (Velocity)
Adapt to change (Re-estimation)

## Slide 11: User Story Modeling
(Who) wants (what) so that (why)
Keep your user stories small
A story is a conversation starter, and gets more detailed over time

## Slide 12: User Story Modeling
GOOD:
Billing wants to see a summary page of all unpaid accounts, so that they can collect payments.
BAD:
Our company wants a new website to increase sales.
Users want rounded corners on the search button.
Good stories satisfy INVEST:
  Independent
  Negotiable
  Valuable
  Estimable
  Small
  Testable

## Slide 13: User Story Modeling: Acceptance Criteria
Story: Users want to import music from a folder so that they can include their own music in the library.
Given a user is on the "Library Folder" screen
When the user clicks Add Then the Add Folder screen shows a radio option for "Search for Music”
When the user saves a folder with "Search for Music" checked Then the folder is added to the list of folders.
Notes: Break for questions about user stories!

## Slide 14: Story Points
… are an arbitrary unit of size/complexity that we use to estimate user stories in lieu of calendar time.
Make all estimates relative to other stories to improve the accuracy of the estimates
An alternative unit: Ideal Days
Notes: Break for questions about story points!

## Slide 15: Planning Poker - Preparation
After all the stories are written, prioritize! We will estimate the high priority stories first.
Pick a baseline story to set the unit size
  Make the smallest story 1 unit OR
  Choose a midsize story
Pick a scale
  Examples: Fibonacci sequence or Powers of 2

## Slide 16: Planning Poker - Gameplay
Have the story owner give a brief overview
Everyone chooses one estimate (KEEP IT SECRET)
On the count of 3, we reveal our estimates!
Do we agree?
YES – We’re done! Move on to the next story.
NO – The high and low outliers defend their positions in a short open discussion
    Record any assumptions we need to make
    Repeat steps 2 - 4 until we (mostly) agree
Notes: Break for questions about Planning Poker!

## Slide 17: Story Backlog
This is just a bucket for all your stories
Keep it prioritized!
Pull estimated stories off this list to create an iteration plan

## Slide 18: Iteration Plan
Usually 2-4 weeks
Do high risk / high priority work first
Make sure everyone can be kept busy
How much can you do in one iteration?
  Compare with previous work, if possible
  If not, guess, it’s OK to be wrong!

## Slide 19: Team Velocity
Velocity is the number of points you completed in previous iterations
Define ‘done’ to include testing and deployment!
Over time this number will stabilize (usually after 3 iterations)
Total Points / Velocity * Iteration length =
Calendar Time!
Notes: Break for questions about Iterations and Velocity!

## Slide 20: Re-estimation
Re-estimate when you have new information that affects your previous estimates
Review your story estimates before each iteration, do they still make sense?
Re-estimate if you change a story
NEVER change an estimate after a story is completed!

## Slide 21: Lab - Planning Poker
Break up into groups
Define roles you will represent:
  Business users (2) and team members (design, dev, QA, etc)
We work at Expedia.com and have 20 million customers. You are doing an add-on for the Customer Service team. Do a planning poker for this user story:
“Customer Service wants to search for customers by their first and last name, so that they can quickly retrieve customer information when on a call.”